## Months
|  |  | Financial Year |  |  | Financial Year | [11 empty] | Financial Year
|  |  | April | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Key Events |  | SHP | Financial Year April: PAC; Financial Year Apr: PAC; Financial Year Apr: PAC
|  | SHP IT | Financial Year Dec: Deployment Freeze; Financial Year Dec: Deployment Freeze
Requirements | Explore and document BU requirements (Phase 1) | ???
Define Ecommerce Operational Model
Define Reference Architecture
Propose Technologies for Reference Architecture
Define Africa Online
Catalog Managment : Define High Level Requirements
Catalog Managment : Identify Solutions
Catalog Managment : Evaluate Solutions
Catalog Managment : Develop Business Case
Internal Search and Navigation : Define High Level Requirements
Internal Search and Navigation: Identify Solutions
Internal Search and Navigation : Evaluate Solutions
Internal Search and Navigation : Develop Business Case
Basket and Checkout : Define High Level Requirements
Basket and Checkout : Identify Solutions
Basket and Checkout : Evaluate Solutions
Basket and Checkout : Develop Business Case
Distributed Order Management : Define High Level Requirements
Distributed Order Management : Identify Solutions
Distributed Order Management : Evaluate Solutions
Distributed Order Management : Develop Business Case
Liquorshop
Business Requrements
Architectureal Requirements
Transpharm Nuco
Business Requrements
Architectureal Requirements
Checkers CFS
Business Requrements
Architectureal Requirements
Architecture | Digital Commerce : Solution Vision | DA | bar: Financial Year May to Financial Year Jun
| Digital Commerce : Solution Architecture (ARIS Models) - Sign Off | DA | bar: Financial Year May to Financial Year Jun
| Digital Commerce : Domain Architecture (Domain Models) - Sign Off | DA / EA | bar: Financial Year May to Financial Year Jun
| Digital Commerce : Key Design Desicisons | DA / EA | bar: Financial Year May to Financial Year Jun
| Digital Commerce : Reference Architecture | DA / EA /DD | bar: Financial Year May
Development | Soure control | DD | bar: Financial Year Jul
| CI / CD Complete | DD | bar: Financial Year Jul
| Design | DD | bar: Financial Year Jul to Financial Year Oct
| Development | DD | bar: Financial Year Jul to Financial Year Oct
| Test | DD | bar: Financial Year Jul to Financial Year Oct
Infrastucture | Build Infrastructure | DD / DA / BLD6 | bar: Financial Year Jul; Financial Year Nov to Financial Year Jan
| QA Infrastructure | DD / DA / BLD7 | bar: Financial Year Aug; Financial Year Nov to Financial Year Jan
| PREP Infrastructure | DD / DA / BLD8 | bar: Financial Year Sep; Financial Year Nov to Financial Year Jan
| Production Infrastruture | DD / DA / BLD9 | bar: Financial Year Oct to Financial Year Jan
People and Process | Onboarding Program Manager | M | bar: Financial Year May
| Onboarding of Domain Architect (Shared) | M | bar: Financial Year April to Financial Year May
| Onboarding of Senior Business analyst | M | bar: Financial Year Jun
DA = Domain Architect
EA = Enterprise Architect
DD = Dimension Data
PM = Project Manager
MC = Mark

## Weeks
Apr 19 - 23 | Apr 26 - 30 | May 03 - 07 | May 10 - 14 | May 03 - 09 | May 17 - 21 | May 24- 28 | May 31- 04 | Jun 07 - 11 | Jun 14- 18 | Jun 21- 25 | Jun 28- 02 | Jul 05 - 09 | Jul 12 - 16 | Jul 19 - 23 | Jul 26 - 30 | Jul 05 - 13 | Jul 05 - 14 | Jul 05 - 15 | Jul 05 - 16 | Jul 05 - 17 | Jul 05 - 18 | Jul 05 - 19 | Jul 05 - 20 | Jul 05 - 21 | Jul 05 - 22

## Notes
In the costing
MVP
| 2021-06-07 | 2021-11-07
Vanilla Hybris
Pulling in products
Pushing out orders
Payment Gateway
No delivery
Bare Bones
UI
CFS
Liquorshop
Fullfillment
Price and availability
KDD
Does the downstream system always use the PIM
Publish and Subscribe from ERP for PIM
UI
- Look what a spartacas
- what payment options
- what can we do from a fullfillment
- How will products will be provisioned